## Status Definitions
Definitions of Status
Status | Definition
On Schedule | The deliverable was not completed during this FY but is on schedule to be complete by the FY that it is due (as indicated by blue cells in the table).
Behind Schedule | The deliverable was not complete during this FY and is behind schedule to be completed by the FY that it is due (as indicated by blue cells in the table).
Completed for FY | The deliverable was completed during the FY but will be due again in future FYs.
Complete | The deliverable was completed during the FY and is completed for the Plan as a whole (not due in future FY)
No Work Scheduled | The deliverable was not completed during this FY because no work was scheduled to be completed during this FY.
DRAFT PROPOSED STATUS STATEMENTS
Complete | Activity was completed during the current year as planned.
On Schedule | Activity is due for completion by current year-end. Work on the activity has commenced and the RP expects to meet the deadline.
Ahead of Schedule | Activity is not due for completion by current year-end but may be completed earlier than planned.
Behind Schedule | Activity is due for completion by current year-end. The RP does not expect the deadline will be met.
No Work Scheduled | Activity was not completed during this current year because no work was scheduled to be completed.

## WATER QUALITY WQ
|  |  |  | ACTIVITY TARGET YR FOR COMPLETION |  |  |  |  | CURRENT YR STATUS | CURRENT YEAR COMMENTS
Water Quality Goals | Water Quality Objectives | Water Quality Goal Attainment Activities | UMRLAC RP | 2026 | 2027 | 2028 | 2029 | 2030 | 2026 | 2026
WATER QUALITY GOAL 1: The upper Merrimack River and its tributaries maintain or exceed their statutory designated uses so that its citizens and visitors can enjoy swimming, fishing, boating, and its communities can depend on reliable clean water sources. | OBJECTIVE: WQ-1 - The UMRLAC will monitor and prioritize state and federal legislation and rules that affect watershed management in the upper Merrimack region and draft comment letters and provide testimony to support water quality. | Seek opportunities to participate in NHDES rule development committees (e.g., Alteration of Terrain and Shoreland Protection Act committees).
Designate an UMRLAC member to monitor key state and federal web sites or contact key personnel on pending rule changes and update full committee at regular meetings.
Monitor legislative review documents to identify upcoming proposed legislation.
| OBJECTIVE: WQ-2 - By end of 2008, all upper Merrimack River public and local officials will be aware of the UMRLAC and the resources that it provides for improving water quality through a meeting with each community at least once per year or by convening training and other events. | Contact local Planning Boards in UMR communities to attend one of their meetings for informational purposes to discuss and share UMMP results, Management Plan recommendations, and survey results comparing zoning ordinances, subdivision, and site plan requirements in each of the communities.
Schedule a follow-up meeting in 2009 or 2010 to share results of additional data gathering efforts conducted as part of this management plan.
| OBJECTIVE: WQ-3 - Encourage consistency in the water quality protection measures and requirements included in local ordinances within the upper Merrimack communities, so that they all have strong, enforceable watershed protection and water quality ordinances in place by 2010 | Coordinate and work with Planning Boards in UMR communities to encourage the inclusion and adoption of NHDES’s recent Draft Stormwater Model Ordinance language (March 2007) in local ordinance and site plan and subdivision regulations to enhance water quality protection measures for future development.
By the end of 2008, compile and make available on merrimackriver.org, a simple guide or other reference documents regarding Best Management Practices targeted to the upper Merrimack communities with particular emphasis on any new NHDES regulations (e.g., AoT Rules, Comprehensive Shoreland Protection Act).
By mid-2009, update and distribute a new State of UMR River Quality Report summarizing recent findings and other relevant information (e.g., water quality, macroinvertebrate data, impervious area estimates) to educate local officials on current conditions and needs for new protection measures.
WATER QUALITY GOAL 2: Restore those portions of the upper Merrimack River and its tributaries that are not meeting their statutory designated uses so that its citizens and visitors can enjoy swimming, fishing, boating, and its communities can depend on reliable clean water sources. | OBJECTIVE: WQ-4 - By mid-2008, all stream reaches or other waterbodies in the upper Merrimack watershed that are listed as impaired on the NH Department of Environmental Services 303(d) list are prioritized for restoration and specific corrective measures identified. | Encourage the development or obtain existing higher resolution aerial photography to identify potential sources of runoff, especially in reaches identified as not supporting their designated uses.
Work with NHDES to generate a map and data tables containing assessment information and impairments for the upper Merrimack River and its tributaries.
Coordinate and participate in the review of the planned upper Merrimack River and Pemigewasset River Study to be directed by NHDES over the next three years from 2007 to 2009, which includes dry and wet weather sampling and modeling pollutant loading along various reaches.
Expand UMMP to increase number of parameter and/or include smaller tributaries to bracket known “hot spots” or verify suspected source areas in reaches not supporting their designated uses especially due to elevated bacteria levels.
Create a map delineating and quantifying the extent of impervious surfaces within each sub-watershed based on GRANIT land use data layer information. Identify watersheds having the largest percent imperviousness and those nearing thresholds that have been found to lead to water quality impacts.
Conduct a baseline annual pollutant loading analysis on a sub-watershed basis using the Center for Watershed Protection “Simple Method” procedure
Investigate continuation of “dry” and “wet weather” sampling conducted in (UM & PR) Study in key locations.
Using existing GIS data layers, identify and provide relative ranking of key areas that have the highest development potential based on road access, development trends, soils, slopes, and other conditions.
Coordinate with CNHRPC and LRRPC to evaluate results of recent or pending build-out analyses.
| OBJECTIVE: WQ-5 - By early 2010, create a restoration plan that identifies, prioritizes, and list sources for funding to implement additional planning, monitoring, and restoration studies or measures to protect water quality and/or aquatic habitat conditions. | Identify and evaluate any similar ongoing or completed restoration plan approaches in other regions of the state.
Identify principal goals and objectives of a restoration plan based on the most recent understanding of the sources, listed impairments and extent of the problem.
lign UMMP sampling, analytical and reporting procedures with NHDES’s Consolidated Assessment Listing Methodology (CALM) for common parameters (e.g., dissolved oxygen, bacteria).
Identify potential sources of funding and in technical assistance in developing and completing the Plan.
Identify areas in local regulations that could be strengthened and improved to assist restoration and preserve future stream integrity conditions.
\]